## L4 Checklist
Clinical Guideline Development L4 Checklist
Label | Item | Description | Item Status | Notes
1. | Publishing Information | Publishing metadata for the content
1.a | Publisher | Who is the publisher? (Name and public contact information)
1.b | Steward | Who is the steward? (Name and public contact information)
2. | Local Prioritization and Selection
2.a | Charter | Project Charter, including high-level approach to evaluation and measurement
2.b | Gap Analysis | Care gap analysis
2.c | Local Feasibility | Local feasibility assessment (harmonization guidelines)
2.d | Guideline Selection | Make decision which guidelines/CDS to implement; assess implementability
2.d.i | Local Applicability | Assess local organizational need/applicability (including GUIDES checklist Domain 1: The CDS context)
2.d.ii | Implementability | Assess intrinsic implementability of guideline (e.g. GLIA v2.0; GUIDES checklist Domain 2: The CDS content)
2.e | Communication | Communicate and market decision to implement
2.f | Incentives | Decide whether to incentivize (and how)
3. | Evaluate Local Context | Evaluate Local Workflow and Context
3.a | Burden | Assess burden
3.b | Workflow | Localize workflows (include “5 rights” of CDS)
3.c | Entry Points | Identify points of entry
3.d | Apply Workflow Template | Apply workflow template to point of entry
3.e | Stakeholder Engagement | Engage stakeholders
4. | Feasibility Assessment (Technical) | Feasibility Assessment (Technical)
4.a | EHR Technical Feasibility | EHR technical feasibility requirements
4.b | Technical Design Strategy | Design technical strategy for local setting (EHR capabilities, interfaces, etc.)
4.c | Measurement Strategy Design | Design measurement strategy (e.g. process measures, outcome measures)
4.d | Update Charter | Update charter with additional details of technical approach and measures
5. | Local Design | Local Design (Localization of new workflow and L3 "tweaks")
5.a | Convene End Users | Convene end users
5.b | “To-be” Workflow | Map “to-be” workflow
5.c | System Architecture | Evaluate and design system architecture
5.d | Design I.T. artifacts/features | Detailed design of localized I.T. artifacts/features
5.e | Localize Measure Capture | Localize measure capture (e.g., what demographic group or other conditions are included in the denominator)
5.f | Start to develop training (localize) | Start to develop training (localize) – make them aware of workflow, etc.
5.g | Consider Multiple EMRs | Consider multiple EMRs; repeat localization design per EMR as needed
6. | Build L4 Artifacts/Features | Build L4 Artifacts/Features: a) in EMR, or b) as web service or app
6.a | Build L4 Artifacts/Features | Build the L4 artifacts/features, e.g., value sets, logic records, rules, alerts
6.b | Build Review | Conduct a build review
6.c | Demonstration | Demo to end users
6.d | Repeat if heterogenous EMRs | Repeat if heterogenous EMR environment (e.g., if there is more than one EMR)
7. | Test and Refine | Test and Refine
7.a | Unit Test | Unit test code/artifacts
7.b | Integrated Test Scripts | Write localized test scripts for integrated testing
7.c | Integrated System Test | Integrated system test, e.g., call out to a Web; systems working together
7.d | Create Test Milieu | Create test milieu (test patients)
7.e | UAT (user acceptance testing) | UAT (user acceptance testing); does the thing it’s needed to do downstream
7.f | Usability Testing | Usability testing e.g., practical issues such as #clicks to get to recs.
7.g | Refine | Revise at all steps
8. | Educate and Train | Educate and Train
8.a | Localize Education/Training | Update education with local EHR design, e.g., screenshots; finish localization of training and who to train; how to best deliver training.
8.b | Tailor Training Strategy | Finish localization of traning and who to train; how best to deliver training including tailoring to usual training channels (multiple pathways)
8.c | Training Policy and Procedures | Develop training policy & procedures
8.d | Train End Users | Train end users on CDS, policy, & procedures
8.e | Update Training | Update and reinforce training based on initial training rounds
9. | Deploy | Deploy
9.a | Migrate Artifacts | Migrate artifacts from Dev to Test to Production
9.b | Go-live Staffing | Plan go-live staffing
9.c | Test Silently | Test with real patients, but behind screen (silently)
9.d | Test in Production | Test in Production by small number of clinicians (e.g.: ~2)
9.e | Readiness | Perform readiness assessment
9.f | Pilot and Provide Feedback | Pilot (e.g. in 2-3 pilot clinics or depts., if multi-clinic organization) and provide feedback
10. | Use Clinically | Use Clinically
10.a | Use System | Use system as designed
10.b | Observation | Observe end users
10.c | Feedback | Provide feedback to users
11. | Measure, Evaluate, and Refine | Measure, Evaluate, and Refine
11.a | Extract Data | Pull data & create reports
11.b | Analyze Data | Analyze and assess per measurement strategy
11.c | Focus groups | Focus groups
11.d | Satisfaction Surveys | Satisfaction surveys built into artifact
11.e | Report Findings | Report findings to leadership and Quality
11.f | Optimize | Iteratively optimize clinical decision artifacts and/or workflows